## Summary Dashboard
PROJECT DELIVERY DASHBOARD — Threat Intelligence Sharing Platform
Total Tasks | Completed | In Progress | Pending | Compliance Controls | Tools Deployed
30 | 26 | 4 | 0 | 18 | 13
Deliverable | Completion %
Architecture & Deployment Docs | 100%
Data Sharing Agreements | 100%
Configuration Guides (RBAC, STIX) | 100%
Automated Analysis Tools | 95%
Integration Manuals | 90%
Reporting Dashboards | 100%
Compliance Documentation | 90%
User Training Guides | 100%

## Implementation Checklist
THREAT INTELLIGENCE SHARING PLATFORM — IMPLEMENTATION CHECKLIST
# | Task Area | Sub-Task | Owner | Status | Notes
1 | 1. Platform Selection & Architecture | Choose MISP as primary CTI platform | Security Architect | Done
2 |  | Deploy OpenCTI for graph correlation layer | Security Architect | Done
3 |  | Design Docker Compose multi-service architecture | DevSecOps | Done
4 |  | Define modular components: ingest, analyze, share, viz | Security Architect | Done
5 | 2. Data Sharing & Governance | Draft Data Sharing Agreement (DSA) template | Legal/Compliance | Done
6 |  | Configure trust models & TLP marking definitions | Security Analyst | Done
7 |  | Implement RBAC for datasets and contribution rights | IAM Engineer | Done
8 | 3. Data Collection & Analysis | Configure IOC / malware sample submission modules | Threat Intel Analyst | Done
9 |  | Implement YARA rule upload & automated scanning | Threat Intel Analyst | Done
10 |  | Set up automated pattern detection engine | Data Engineer | Done
11 |  | Normalize data across sources (STIX objects) | Data Engineer | Done
12 | 4. Standards & Interoperability | Configure TAXII 2.1 server on MISP | Integration Engineer | Done
13 |  | Connect OpenCTI STIX2 feeds to MISP | Integration Engineer | Done
14 |  | Validate SIEM / SOAR / IDS-IPS connector compatibility | Integration Engineer | In Progress
15 | 5. Security & Privacy Controls | Apply AES-256 encryption for data at rest (LUKS/DB) | Security Engineer | Done
16 |  | Enforce TLS 1.3 for all inter-service communication | Security Engineer | Done
17 |  | Implement PII anonymization pipeline (MISP warninglist) | Privacy Officer | Done
18 | 6. Authentication & Authorization | Enable TOTP-based MFA for all platform accounts | IAM Engineer | Done
19 |  | Integrate Keycloak SSO with MISP and OpenCTI | IAM Engineer | In Progress
20 |  | Configure RBAC groups and permission scopes | IAM Engineer | Done
21 | 7. Integration & Collaboration | Connect TheHive for incident case management | SOC Engineer | Done
22 |  | Link MISP events to TheHive alerts via n8n automation | SOC Engineer | Done
23 |  | Enable discussion forums and collaborative tagging | Platform Admin | Done
24 | 8. Monitoring & Reporting | Set up ELK Stack for activity log indexing | Platform Admin | Done
25 |  | Create Kibana dashboards for sharing trends | Data Engineer | Done
26 |  | Configure alerting on anomalous user behaviour | SOC Engineer | In Progress
27 | 9. Compliance & Regulatory | Map MISP data handling to GDPR requirements | Compliance Officer | Done
28 |  | Align platform controls to ISO 27001 Annex A | Compliance Officer | Done
29 |  | Map controls to NIST CSF Identify/Protect/Detect | Compliance Officer | Done
30 |  | Prepare governance docs for compliance audit | Compliance Officer | In Progress

## RBAC Matrix
ROLE-BASED ACCESS CONTROL (RBAC) MATRIX — MISP + OpenCTI Platform
Role ↓ / Permission → | View Public Events | View Restricted Events | Submit IOCs | Submit Malware Samples | Submit YARA Rules | Approve/Publish Events | Manage Users | Configure Feeds | View Reports | Export STIX/TAXII | Delete/Modify Events | Admin Settings
Guest / Read-Only | ✓ | — | — | — | — | — | — | — | ✓ | — | — | —
Analyst | ✓ | ✓ | ✓ | — | — | — | — | — | ✓ | ✓ | — | —
Senior Analyst | ✓ | ✓ | ✓ | ✓ | ✓ | — | — | — | ✓ | ✓ | — | —
Threat Intel Lead | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | — | ✓ | ✓ | ✓ | ✓ | —
SOC Engineer | ✓ | ✓ | ✓ | ✓ | — | — | — | ✓ | ✓ | ✓ | — | —
Platform Admin | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
CISO / Executive | ✓ | ✓ | — | — | — | — | — | — | ✓ | ✓ | — | —

## Compliance Mapping
COMPLIANCE MAPPING — GDPR ¦ ISO 27001 ¦ NIST CSF
Framework | Control Ref. | Requirement | Platform Control | Evidence / Artifact | Status
GDPR | Art. 5 | Data minimisation & accuracy | IOC anonymisation pipeline, warninglist filters | MISP Anonymisation Config Guide | Compliant
GDPR | Art. 17 | Right to erasure | Event hard-delete API, audit log | Deletion Procedure SOP | Compliant
GDPR | Art. 25 | Privacy by design | Encrypted DB, TLS 1.3, minimal PII in events | Architecture Doc §5 | Compliant
GDPR | Art. 32 | Security of processing | AES-256 at rest, TLS in transit, MFA | Security Controls Doc | Compliant
ISO 27001 | A.5.1 | Information security policies | Platform governance framework | Data Sharing Agreement | Compliant
ISO 27001 | A.6.1 | Internal organisation roles | RBAC matrix with named roles | RBAC Configuration Guide | Compliant
ISO 27001 | A.8.1 | Inventory of assets | OpenCTI asset knowledge graph | OpenCTI Entity Catalogue | Compliant
ISO 27001 | A.9.1 | Access control policy | Keycloak SSO + RBAC + MFA | Auth Config Guide | Compliant
ISO 27001 | A.10.1 | Cryptographic controls | AES-256 + TLS 1.3 + LUKS | Encryption Spec §5 | Compliant
ISO 27001 | A.12.4 | Logging & monitoring | ELK audit log, Kibana dashboards | Monitoring Config Guide | Compliant
ISO 27001 | A.13.1 | Network security controls | Docker network segmentation, Nginx proxy | Network Architecture Diagram | Compliant
ISO 27001 | A.16.1 | Incident management | TheHive IR platform integration | Integration Manual §7 | Compliant
NIST CSF | ID.AM | Asset management | OpenCTI entity graph + MISP tags | Asset Inventory Sheet | Compliant
NIST CSF | PR.AC | Identity management & access control | Keycloak + RBAC + MFA | Auth Config Guide | Compliant
NIST CSF | PR.DS | Data security | AES-256, TLS 1.3, anonymisation | Security Controls Doc | Compliant
NIST CSF | DE.CM | Continuous monitoring | ELK + Kibana + alert rules | Monitoring Config Guide | Compliant
NIST CSF | RS.AN | Analysis / response | TheHive + MISP correlation | Integration Manual §7 | Compliant
NIST CSF | RC.RP | Recovery planning | Backup procedures + DR plan | DR & Backup SOP | In Progress

## Tool Inventory
OPEN-SOURCE TOOL INVENTORY — Threat Intelligence Sharing Platform
Tool | Version | Role | Port / Endpoint | License | Docker Image | Status
MISP | 2.4.x | Primary CTI sharing platform | 443 (HTTPS) | AGPL-3.0 | ghcr.io/misp/misp | Deployed
OpenCTI | 6.x | Graph-based CTI correlation | 8080 (HTTP) | Apache-2.0 | opencti/platform:latest | Deployed
TheHive | 5.x | Incident response & case mgmt | 9000 (HTTP) | AGPL-3.0 | strangebee/thehive:latest | Deployed
Cortex | 3.x | Automated analysis engine | 9001 (HTTP) | AGPL-3.0 | thehiveproject/cortex:latest | Deployed
Elasticsearch | 8.x | Log & CTI data indexing | 9200 (HTTP) | Apache-2.0 | elasticsearch:8.x | Deployed
Kibana | 8.x | Analytics & reporting dashboards | 5601 (HTTP) | Apache-2.0 | kibana:8.x | Deployed
Logstash | 8.x | Log pipeline / normalisation | 5044 (TCP) | Apache-2.0 | logstash:8.x | Deployed
Keycloak | 24.x | SSO, MFA, RBAC identity provider | 8180 (HTTP) | Apache-2.0 | quay.io/keycloak/keycloak:latest | Deployed
Nginx | 1.25.x | Reverse proxy / TLS termination | 80, 443 | BSD-2 | nginx:alpine | Deployed
PostgreSQL | 16.x | Persistent DB (OpenCTI, TheHive) | 5432 (TCP) | PostgreSQL | postgres:16-alpine | Deployed
Redis | 7.x | Caching & queue (OpenCTI) | 6379 (TCP) | BSD-3 | redis:7-alpine | Deployed
MinIO | RELEASE.* | S3-compatible object storage | 9000 (API) | AGPL-3.0 | minio/minio:latest | Deployed
TAXII Server (MISP) | built-in | STIX/TAXII 2.1 feed endpoint | 443/taxii/ | AGPL-3.0 | (MISP built-in) | Deployed
Yeti | 2.x | IOC repository & enrichment | 8080 (HTTP) | Apache-2.0 | yeti-platform/yeti:latest | Optional
Wazuh | 4.x | SIEM / log analysis integration | 55000 (API) | GPL-2.0 | wazuh/wazuh-manager | Optional